## Sheet1
NO | Risk Type | Risk Description | Probability | Influence | Risk Solution
1 | Requirements Analysis Risk | The members don't understand the requirements clearly or miss some necessary functional requirements. | 10% | Serious | At the beginning of the project, we spend a lot of time to read meterials、communicate with teacher and make a perfect requirement specification and plan to guide the following design and implementations.
2 | Schedule Risk | Our team consists of two members, and time is not enough because we still have classes and homework for other courses. | 40% | Serious | We have to start the project as early as possible, and take use of tiny piece of time to read meterials to familiar with requirements and make a complete plan. In the weekend, the whole team gather together to communicate and implement step by step.
3 | Ability Risk | Team members' abilities,including self-learning ability、cooperation and stress tolerance have a great impact on the progress of the project and the quality of the project. | 20% | Serious | When meeting some problems, ask for teacher、friends and books in time. And communicates with each other frequently, respects others' thoughts and encourages each other to keep on.
4 | Equipment Risk | Our equipment only has two computers, which may loss control sometimes and run at a slow speed, that is a big trouble to our development. | 10% | Serious | To be patient and if the computer meets some problems, we can do other things such as make plans and read meterials firstly and ask for professional persons to repair.
5 | Technical Risk | The technical risk refers to the document writing and programming. If one of the two is not easy to understand and modify, that is not a perfect system. | 20% | Serious | Most important step is to clear the requirements and form a instructive requirement specification. Accrording to the requirements, draw the UML diagrams logically and then to design to code. Do the works step by step and logically, also carefully and absorbed.